## Sheet1
ID | TASK NAME | PREDECOSSORS | Duration | Jul 23'06 | [5 empty] | Jul 30'06 | [6 empty] | August 06'6
|  |  |  | S | M | T | W | T | F | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | Start |  | 0 days
2 | project proposal document | 1 | 4 days
3 | product requirements documents | 1 | 5.33 days
4 | design | 2 | 5.17 days
5 | implementation(terminal version) | 1 | 6.33 days
6 | implementation(android studio version) | 3.4 | 5.17 days
7 | verifivation | 5 | 4.5 days
8 | maintainance | 6 | 5.17 days
9 | Finish | 7.8 | 0 days